## Sheet1
		Project Charter of EZ Cart

WBS	Modules	Milestones	Task	Subtask	Status	Duration

1	Documentation
1.1	Software Requirement Specification	To depict all application requirements	Documentation			6 hours
			Project Scope			2 hours
			Functional Requirements
			Non Func. Requirements

1.2	Data Dictionary	To describe constraints and dependancies of all tables in the database				1.5 hours

1.3	Class Description	To describe the classes and their members				1.5 hours

1.4	Database Design	DB Design and Data Dictionary				2 hours

1.4	Test Case	To depict whether a module is functioning as desired or not				1 hour

2	Implementation
						2 hour
2.1	Make Database	Make tables in Database

2.2	UI	UI of all pages				10 hours

2.3	Login	To check credentials of a user	Registration of new user	Accept new user's information		30mins
			Login User	Accept and check password		1 hour
			Validation for Registration and login form			1 hour

2.4	Forget Password	To Reset new password	Ask Username			1.5 hours
			Ask email Id

2.5	Normal User	Functions of registered users	Search Item			3 hours
			View Items			2 hours
			Add to cart			2 hour
			Remove from cart			2 hours
			Menubar for categories			1 hour
			Prepare Bill for all cart item			2 hours
			Edit Profile			1 hour

2.6	Admin User	Functions of Admin	Add to Product	Enter all the details of new product		2 hour
				Validate for this add to product form		1 hour
			Edit Product	Enter new updated information		2 hour
			Manage User	Details of all user		3 hours
2.7	Guest User		View Items			2 hours
			Search Item			2 hour

2.8	Testing	To check the application for errors and bugs	Testing based on test-cases			4 hours